## How to use
Sahai v1 — Acceptance Tests
Purpose | Pass/fail checks for every rule in the PRD. A milestone is done when all its Must tests pass (PRD section 16).
Source | GTD AI (Sahai) PRD. The PRD § column names the section each test checks.
Columns you edit | Status, Tested on and Notes (shaded yellow on the Tests tab). Everything else is the test definition.
Status values | Not run · Pass · Fail · Blocked (pick from the dropdown).
Priority | Must = required for the milestone to be done. Should = expected, can slip one milestone.
Checked by | Founder = testable by using the app. Developer = needs the database, logs or tools to verify.
Example entry | Status: Fail · Tested on: 2026-11-03 · Notes: 1.2 appeared only after restarting the app
Default settings assumed | Day starts at 4:00 AM · Presets: Tonight 8 PM, Tomorrow morning 8 AM, 3 days later 8 AM, Next week Monday 8 AM · Recurring items show 3 days early · Reminder time 9:00 AM · Undo window 5 seconds (all from the PRD).
Dates used | Examples use November 2026 (Nov 1 is a Sunday). The four credit card bills follow PRD section 7: HDFC 5th, SBI 12th, ICICI 18th, Axis 25th.
Weekly cycle | Re-run Fail and Blocked tests after each build, plus every Must test of the current milestone. Re-run all Must tests before the tester trial.

## Summary
Milestone | Name | Tests | Must | Pass | Fail | Blocked | Not run | % passed | Musts passed | Milestone done?
M1 | Foundations | 12 | 11 | 0 | 0 | 0 | 12 | 0% | 0 | Not yet
M2 | Core loop | 20 | 17 | 0 | 0 | 0 | 20 | 0% | 0 | Not yet
M3 | Set aside | 28 | 22 | 0 | 0 | 0 | 28 | 0% | 0 | Not yet
M4 | Recurring items | 22 | 17 | 0 | 0 | 0 | 22 | 0% | 0 | Not yet
M5 | Groups and order | 12 | 9 | 0 | 0 | 0 | 12 | 0% | 0 | Not yet
M6 | Capture | 10 | 9 | 0 | 0 | 0 | 10 | 0% | 0 | Not yet
M7 | Polish and safety | 16 | 7 | 0 | 0 | 0 | 16 | 0% | 0 | Not yet
M8 | Release prep | 4 | 3 | 0 | 0 | 0 | 4 | 0% | 0 | Not yet
Total | v1 | 124 | 95 | 0 | 0 | 0 | 124 | 0% | 0 | Not yet
All counts are formulas over the Tests tab; a milestone is done when every Must test passes (PRD section 16).

## Tests
ID | Milestone | Area | PRD § | Scenario | Given | When | Then | Priority | Checked by | Status | Tested on | Notes
AT-001 | M1 | Tree structure | 4, 8.4 | Create every node type | A fresh install with no data | The user creates a domain, a stream, a stream item, a project, a task and a subtask in the Explorer | Each appears under its parent with the right type and stays after closing and reopening the app | Must | Founder | Not run
AT-002 | M1 | Tree structure | 4 | Only valid children can be added | A domain, a stream, a project, a task, a subtask and a stream item exist | The user opens the add menu on each | Domain offers stream or project; stream offers stream item only; project offers task only; task offers subtask only; subtask and stream item offer nothing | Must | Founder | Not run
AT-003 | M1 | Tree structure | 4, 5 | Domains and streams have no status | A domain and a stream exist | The user opens each one's options in the Explorer | Neither offers a checkmark or Mark done | Must | Founder | Not run
AT-004 | M1 | Ordering | 8.4 | Reorder sequential tasks | A project has Task 1, Task 2 and Task 3 | The user moves Task 3 above Task 1 | The order reads Task 3, Task 1, Task 2, and stays that way after restarting the app | Must | Founder | Not run
AT-005 | M1 | Ordering | 8.4 | Reorder subtasks and stream items | A task has Subtasks A, B, C and a stream has Items X, Y, Z | The user moves C to the top and Z to the top | Orders read C, A, B and Z, X, Y, and persist after restart | Must | Founder | Not run
AT-006 | M1 | Tree structure | 8.4 | Move an item to another parent | Subtask S sits under Task A; Task B is in the same project | The user moves S to Task B | S appears under Task B and no longer under Task A | Should | Founder | Not run
AT-007 | M1 | Locks | 4, 8.4 | Locked tasks are marked | A project has Task 1 (TODO) and Task 2 (TODO) | The user views the project in the Explorer | Task 2 is visibly marked as locked; Task 1 is not | Must | Founder | Not run
AT-008 | M1 | Delete | 7 | Delete with Undo | A project with three tasks exists | The user deletes the project, then taps Undo within 5 seconds | The project and all three tasks are back exactly as before | Must | Founder | Not run
AT-009 | M1 | Delete | 5, 7 | Deleted items vanish but stay in the database | A project was deleted and the Undo window has passed | The user checks every screen; the developer inspects the database | The project and its tasks appear nowhere in the app; their rows still exist with is_deleted = true | Must | Developer | Not run
AT-010 | M1 | Data | 3, 10 | Sync-ready fields are set | Any new node is created | The developer inspects its row, then the user edits its title | The id is a UUID; updated_at is a UTC time and changes after the edit | Must | Developer | Not run
AT-011 | M1 | Data | 3, 13 | No Internet permission in v1 | The v1 release build is installed | The user opens the app's info page in Android settings | No Internet (network) permission is listed | Must | Founder | Not run
AT-012 | M1 | Data | 13 | Schema migration keeps data | A build with real data is installed | A newer build with a schema change is installed over it | All data is intact, and a copy of the old database was made before migrating | Must | Developer | Not run
AT-013 | M2 | Visibility | 6 | Only the first subtask shows | Project P has Task 1 with Subtasks 1.1 and 1.2, all TODO | The user opens the Summary | Only 1.1 shows from Project P | Must | Founder | Not run
AT-014 | M2 | Visibility | 6 | A task with no subtasks shows directly | Project P's Task 1 has no subtasks | The user opens the Summary | Task 1 shows as a card | Must | Founder | Not run
AT-015 | M2 | Progression | 6, 7 | Next subtask surfaces | 1.1 is showing on the Summary; 1.2 is hidden | The user marks 1.1 done | 1.1 leaves the Summary and 1.2 appears | Must | Founder | Not run
AT-016 | M2 | Progression | 6, 7 | Task surfaces for sign-off | 1.2 is the last TODO subtask of Task 1 | The user marks 1.2 done | Task 1 appears as a sign-off card and is still TODO | Must | Founder | Not run
AT-017 | M2 | Progression | 6 | Next task unlocks after sign-off | Task 1 is showing for sign-off; Task 2 has Subtasks 2.1 and 2.2 | The user marks Task 1 done | 2.1 appears; nothing else from Task 2 shows | Must | Founder | Not run
AT-018 | M2 | Visibility | 6 | Locked tasks never show | Task 1 is TODO; Task 2 has subtasks | The user opens the Summary | Nothing from Task 2 appears | Must | Founder | Not run
AT-019 | M2 | Visibility | 6 | Empty project prompts for tasks | A new project has no tasks | The user opens the Summary | The project appears as a card prompting the user to add tasks | Must | Founder | Not run
AT-020 | M2 | Visibility | 6 | Project sign-off | Every task in Project P is DONE | The user opens the Summary, then marks Project P done | Project P appears for sign-off; after marking it done nothing from P shows | Must | Founder | Not run
AT-021 | M2 | Visibility | 6 | Domains and streams never appear | An empty domain and an empty stream exist | The user opens the Summary | Neither appears as a card | Must | Founder | Not run
AT-022 | M2 | Visibility | 6 | One normal stream item at a time | A stream has normal items A, B and C in that order | The user opens the Summary, then marks A done | Only A shows at first; after A is done, only B shows | Must | Founder | Not run
AT-023 | M2 | Visibility | 6 | At most one card per project | A project has three tasks, each with subtasks | The user works through several items over time | The Summary never shows more than one card from that project | Must | Founder | Not run
AT-024 | M2 | Visibility | 5, 6 | Deleted children don't block the parent | Task 1 has Subtask 1.1 DONE and Subtask 1.2 TODO | The user deletes 1.2 | Task 1 appears for sign-off | Must | Founder | Not run
AT-025 | M2 | Undo | 7 | Undo a completion | 1.1 is showing and 1.2 is hidden | The user marks 1.1 done and taps Undo within 5 seconds | 1.1 is TODO and showing again; 1.2 is hidden again | Must | Founder | Not run
AT-026 | M2 | Undo | 7 | Undo window closes | The user just marked an item done | 5 seconds pass without tapping Undo | The snackbar disappears and the item stays DONE | Should | Founder | Not run
AT-027 | M2 | Reopen | 7 | Reopening a child reopens its ancestors | Task 1 and all its subtasks are DONE | The user reopens Subtask 1.2 in the Explorer | 1.2 and Task 1 are both TODO, and 1.2 shows on the Summary | Must | Founder | Not run
AT-028 | M2 | Reopen | 7 | Reopening an earlier task re-locks later ones | Task 1 is DONE; Task 2 is current with 2.1 DONE and 2.2 TODO | The user reopens Task 1, then later marks it done again | Task 1 shows and nothing from Task 2 does; after Task 1 is done, 2.2 shows and 2.1 is still DONE | Must | Founder | Not run
AT-029 | M2 | Summary | 8.2 | Tapping a card shows its path | A subtask card is showing | The user taps it | The path Domain › Project › Task appears with an Open in tree option that opens it in the Explorer | Should | Founder | Not run
AT-030 | M2 | Activity log | 9 | Completion is logged | A subtask is showing | The user marks it done | A completed event is stored with node id and type, domain, group, UTC time and time-zone offset | Must | Developer | Not run
AT-031 | M2 | Activity log | 9 | Surfacing is logged | 1.1 is showing and 1.2 is hidden | The user marks 1.1 done | A surfaced event is stored for 1.2 | Must | Developer | Not run
AT-032 | M2 | Activity log | 9 | Create, delete, restore and reopen are logged | A project exists | The user adds a task, deletes it, taps Undo, completes it, then reopens it | created, deleted, restored, completed and reopened events are stored in that order | Should | Developer | Not run
AT-033 | M3 | Set aside | 6, 7 | Setting aside a subtask surfaces the next | 1.1 is showing; 1.2 is TODO | The user sets 1.1 aside until Tonight with the default scope | 1.1 disappears and 1.2 appears | Must | Founder | Not run
AT-034 | M3 | Set aside | 6 | A waking subtask takes its place back | 1.1 is set aside until 5:00 PM and 1.2 is showing | 5:00 PM passes while the app is open | 1.1 shows and 1.2 is hidden, without the user doing anything | Must | Founder | Not run
AT-035 | M3 | Set aside | 6 | All subtasks set aside darkens the branch | 1.1 and 1.2 are the only TODO subtasks of Task 1, and both are set aside | The user opens the Summary | Nothing from Project P shows, and Task 1 does not appear | Must | Founder | Not run
AT-036 | M3 | Set aside scope | 7 | Scope options match the card type | A subtask, a task, a project and a stream item card are showing | The user opens Set aside on each | Scope defaults to the item itself. Subtask offers its task, project or domain; task offers its project or domain; project offers its domain; stream item offers its stream or domain | Must | Founder | Not run
AT-037 | M3 | Set aside scope | 6, 7 | Scope: its task | 1.1 is showing | The user sets it aside with scope Its task until tomorrow 8 AM | Nothing from Task 1 shows; only Task 1 holds the wake time; at 8 AM, 1.1 shows again | Must | Founder | Not run
AT-038 | M3 | Set aside scope | 6, 7 | Scope: its project | A subtask from Project P is showing | The user sets it aside with scope Its project | Nothing from Project P shows; only Project P holds the wake time | Must | Founder | Not run
AT-039 | M3 | Set aside scope | 6, 7 | Scope: its domain | Domain Freelance has Project A, Project B and Stream S, each showing a card | The user sets aside a card from Project A with scope Its domain | No cards from A, B or S show, and the Set-Aside page lists Freelance | Must | Founder | Not run
AT-040 | M3 | Set aside | 6 | A set-aside current task stalls its project | Task 1 (no subtasks) is current; Task 2 is next | The user sets Task 1 aside | Task 2 does not appear until Task 1 wakes and is done | Must | Founder | Not run
AT-041 | M3 | Set aside | 7, 8.4 | Set aside from the Explorer | A stream with three items is in the Explorer | The user sets the stream aside until Next week | None of its items show on the Summary until it wakes | Must | Founder | Not run
AT-042 | M3 | Presets | 7 | Default preset times | It is 3:00 PM on Tuesday, Nov 3 | The user opens the set-aside presets | Tonight = Nov 3 8 PM; Tomorrow morning = Nov 4 8 AM; 3 days later = Nov 6 8 AM; Next week = Mon Nov 9 8 AM | Must | Founder | Not run
AT-043 | M3 | Presets | 7 | Day starts at 4 AM | Day starts at is 4:00 AM and it is 1:30 AM on Wednesday, Nov 4 | The user picks Tomorrow morning | The wake time is Nov 4 at 8 AM, later that same morning | Must | Founder | Not run
AT-044 | M3 | Presets | 7 | Past presets are hidden | It is 11:00 PM | The user opens the presets | Tonight is not offered | Must | Founder | Not run
AT-045 | M3 | Presets | 7 | Custom picker blocks past times | The custom date and time picker is open | The user tries to choose a time earlier than now | The time can't be selected | Must | Founder | Not run
AT-046 | M3 | Set-Aside page | 8.3 | Set-Aside page lists items | Three items are set aside until different times | The user opens the Set-Aside page | All three are listed soonest first, each with title, path, wake time and time remaining | Must | Founder | Not run
AT-047 | M3 | Set-Aside page | 8.3 | Hidden descendants sit under their ancestor | Project P is set aside; none of its tasks are set aside themselves | The user opens the Set-Aside page | Project P is listed once; its tasks are not listed separately | Should | Founder | Not run
AT-048 | M3 | Set-Aside page | 7, 8.3 | Wake now | An item is set aside until next week | The user taps Wake now | It shows on the Summary straight away and leaves the Set-Aside page | Must | Founder | Not run
AT-049 | M3 | Set-Aside page | 8.3 | Change time | An item is set aside until next week | The user changes its time to tomorrow 8 AM | The Set-Aside page shows the new time and the item wakes then | Should | Founder | Not run
AT-050 | M3 | Notifications | 7 | Grouped wake notification | Three items are set aside until the same time and the app is closed | That time arrives | One notification says 3 items are back and expands to list the three titles; tapping it opens the Summary | Must | Founder | Not run
AT-051 | M3 | Notifications | 7 | A single waking item is named | Call Rahul is the only item set aside until tomorrow 9:00 AM, and the app is closed | 9:00 AM arrives | One notification reads Call Rahul is back; tapping it opens that item on the Summary | Must | Founder | Not run
AT-052 | M3 | Notifications | 7 | Different wake times notify separately | One item is set aside until 8:00 AM and another until 9:00 AM | Both times pass | Two separate notifications arrive, one at each time | Should | Founder | Not run
AT-053 | M3 | Notifications | 7 | Remind me off wakes quietly | The user opens the set-aside picker on a card | The user sees Remind me switched on, turns it off, and sets the item aside until 5:00 PM | At 5:00 PM no notification is posted, but the item reappears on the Summary | Must | Founder | Not run
AT-054 | M3 | Notifications | 6, 7 | No notification when still hidden | A subtask is set aside until 9:00 AM tomorrow and its domain is set aside until next week | 9:00 AM arrives | No notification is posted and the subtask does not appear on the Summary | Must | Founder | Not run
AT-055 | M3 | Notifications | 7 | Permission asked at first set aside | A fresh install on Android 13 or higher | The user opens the app, then sets aside an item for the first time | No permission prompt at first launch; the notification prompt appears at the first set aside | Must | Founder | Not run
AT-056 | M3 | Notifications | 7, 8.6 | Notifications can be turned off | Notifications are off in Settings and an item is set aside | Its wake time passes | No notification is posted, but the item still reappears on the Summary | Should | Founder | Not run
AT-057 | M3 | Notifications | 7 | Reminders survive a restart | An item is set aside until tomorrow 8 AM | The phone is restarted | The reminder still arrives | Must | Founder | Not run
AT-058 | M3 | Notifications | 7 | Exact reminders | Exact reminders is on and Android's alarm permission is granted | A set-aside time arrives | The notification arrives within a minute of the wake time | Should | Founder | Not run
AT-059 | M3 | Activity log | 9 | Set aside is logged | A subtask is showing | The user sets it aside with scope Its project using the Tonight preset | A set_aside event stores the wake time, the preset, the scope level and whether Remind me was on | Must | Developer | Not run
AT-060 | M3 | Activity log | 9 | Waking is logged | Two items are set aside until tomorrow | One wakes at its time; the user taps Wake now on the other | Each gets a woke event, one marked automatic and one marked Wake now | Should | Developer | Not run
AT-061 | M4 | Recurring | 7 | Appears 3 days before due | HDFC card repeats monthly on the 5th with the default 3-day lead; next due Nov 5 | The date moves from Nov 1 to Nov 2 | HDFC is absent on Nov 1 and appears at the start of Nov 2 labelled Due Nov 5 | Must | Founder | Not run
AT-062 | M4 | Recurring | 7 | Due today label | HDFC is due Nov 5 and unpaid | It is any time on Nov 5, before Nov 6 at 4:00 AM | The card reads Due today | Must | Founder | Not run
AT-063 | M4 | Recurring | 7 | Overdue label | HDFC is due Nov 5 and unpaid; Day starts at is 4:00 AM | Nov 6 at 4:00 AM passes, then Nov 9 arrives | The card reads 1 day overdue on Nov 6 and 4 days overdue on Nov 9 | Must | Founder | Not run
AT-064 | M4 | Recurring | 6, 7 | An unpaid bill doesn't hide the next | Finance & Bills holds HDFC (due 5th) and SBI (due 12th); HDFC is unpaid | The date becomes Nov 9 | Both cards show: HDFC as 4 days overdue and SBI as Due Nov 12 | Must | Founder | Not run
AT-065 | M4 | Recurring | 6 | Recurring items never block normal items | Stream Home holds Electricity bill (recurring, first), Fix the tap and Buy curtains (normal) | The electricity bill is due | Electricity bill and Fix the tap both show; Buy curtains stays hidden | Must | Founder | Not run
AT-066 | M4 | Recurring | 7 | Completing schedules the next occurrence | HDFC due Nov 5 is showing | The user marks it done on Nov 3 | The card leaves; HDFC stays TODO with next due Dec 5 and reappears on Dec 2 | Must | Founder | Not run
AT-067 | M4 | Recurring | 7 | Paying late keeps the schedule | HDFC repeats from the due date and is due Nov 5 | The user marks it done on Nov 7 | The next due date is Dec 5, not Dec 7 | Must | Founder | Not run
AT-068 | M4 | Recurring | 7 | A missed cycle shows straight away | HDFC due Nov 5 was never paid | The user marks it done on Dec 10 | HDFC immediately shows again, due Dec 5 and 5 days overdue | Must | Founder | Not run
AT-069 | M4 | Recurring | 7 | Repeat from completion date | Haircut repeats every 4 weeks from completion, with a 3-day lead | The user marks it done on Nov 10 | Next due is Dec 8, and the card appears on Dec 5 | Must | Founder | Not run
AT-070 | M4 | Recurring | 7 | Undo a recurring completion | HDFC due Nov 5 is showing | The user marks it done and taps Undo within 5 seconds | HDFC is back on the Summary, still due Nov 5 | Must | Founder | Not run
AT-071 | M4 | Recurring | 7, 9 | Skip this occurrence | HDFC due Nov 5 is showing | The user taps Skip this occurrence | Next due becomes Dec 5; a skipped event is logged and no completed event | Must | Founder | Not run
AT-072 | M4 | Recurring | 7 | Setting aside keeps the schedule | HDFC due Nov 5 is showing on Nov 2 | The user sets it aside until Nov 4 at 8 AM | It returns Nov 4 at 8 AM still labelled Due Nov 5, and the following due date is still Dec 5 | Must | Founder | Not run
AT-073 | M4 | Recurring | 7 | Missing month days fall on the last day | An item repeats monthly on the 31st | The schedule reaches November and February | It is due Nov 30 and Feb 28, 2027 | Must | Founder | Not run
AT-074 | M4 | Recurring | 7 | Weekly on chosen weekdays | An item repeats weekly on Monday and Thursday | The user completes Monday's occurrence | The next due date is that Thursday | Should | Founder | Not run
AT-075 | M4 | Recurring | 7 | Interval schedules | An item repeats every 2 weeks from the due date, due Nov 5 | The user completes it | The next due date is Nov 19 | Should | Founder | Not run
AT-076 | M4 | Recurring | 7 | Yearly schedules | An item repeats yearly on Mar 15 | The user completes the 2027 occurrence | The next due date is Mar 15, 2028 | Should | Founder | Not run
AT-077 | M4 | Recurring | 5, 8.4 | Recurring items never stay DONE | HDFC was just completed | The user opens it in the Explorer | It shows as TODO with its next due date, not as DONE | Must | Founder | Not run
AT-078 | M4 | Notifications | 7 | Recurring reminders use the reminder time | HDFC appears on Nov 2; reminder time is 9:00 AM | Nov 2 and Nov 5 arrive with HDFC unpaid | Notifications arrive at 9:00 AM on Nov 2 and on Nov 5, not at 4:00 AM | Must | Founder | Not run
AT-079 | M4 | Notifications | 7 | Due reminder fires inside a paused domain | Personal is set aside until Nov 10; HDFC (in Personal) is due Nov 5 | Nov 5 at 9:00 AM arrives | HDFC is not on the Summary, but the due-date reminder fires; tapping it opens HDFC so it can be marked done | Must | Founder | Not run
AT-080 | M4 | Recurring | 7 | Stop repeating | HDFC is a recurring item in a stream with normal items | The user turns off repeating | Its due date is cleared and it follows the one-at-a-time rule like a normal stream item | Should | Founder | Not run
AT-081 | M4 | Recurring | 7 | Due dates follow the phone's time zone | HDFC is due on the 5th; the phone moves from India to Dubai time | The user checks the card on the 5th local time | It reads Due today on the local 5th | Should | Founder | Not run
AT-082 | M4 | Activity log | 9 | Recurring completion stores the due date | HDFC is due Nov 5 | The user marks it done on Nov 7 | The completed event stores the due date Nov 5 | Must | Developer | Not run
AT-083 | M5 | Groups | 8.2 | Ungrouped cards use the default list | No context groups exist | The user opens the Summary | All cards appear in the default list | Must | Founder | Not run
AT-084 | M5 | Groups | 8.2 | Create a group | No groups exist | The user creates At laptop with an icon | At laptop is available to assign and shows on the Summary once it holds a card | Must | Founder | Not run
AT-085 | M5 | Groups | 8.2 | Groups are inherited | At laptop is set on Project P; its tasks and subtasks have no group | A card from P shows | The card appears under At laptop | Must | Founder | Not run
AT-086 | M5 | Groups | 8.2 | The nearest group wins | At laptop is set on Project P and Errands on Subtask 1.2 | 1.2 surfaces | 1.2 appears under Errands | Must | Founder | Not run
AT-087 | M5 | Groups | 8.2 | Dragging assigns that item only | 1.1 shows under At laptop, inherited from Project P | The user drags 1.1 to Errands, then later marks it done | 1.1 sits in Errands; when 1.2 surfaces it appears under At laptop | Must | Founder | Not run
AT-088 | M5 | Order | 8.2 | The next card keeps the same position | At laptop shows X, then 1.1 from Project P, then Y | The user marks 1.1 done and 1.2 (same group) appears | At laptop shows X, 1.2, Y | Must | Founder | Not run
AT-089 | M5 | Order | 8.2 | A card moving groups goes to the end | 1.2 has Errands set on it; 1.1 shows under At laptop | The user marks 1.1 done | 1.2 appears at the end of Errands | Must | Founder | Not run
AT-090 | M5 | Order | 8.2 | New slots go to the end | At laptop already holds three cards | The user creates a new project with At laptop set | Its card appears at the end of At laptop | Should | Founder | Not run
AT-091 | M5 | Order | 8.2 | Recurring items keep their position | The user placed HDFC second in its group | HDFC is completed and reappears next month | It returns in the second position | Should | Founder | Not run
AT-092 | M5 | Order | 8.2 | Dragging never changes the tree | The user rearranges cards on the Summary | The user opens the Explorer | The tree order is unchanged | Must | Founder | Not run
AT-093 | M5 | Order | 8.2 | Summary order persists | The user arranged the Summary | The app is closed and reopened | The arrangement is the same | Must | Founder | Not run
AT-094 | M5 | Activity log | 9 | Reorders and group changes are logged | Cards are showing | The user drags a card within a group, then to another group | reordered events store old and new position and group; a group_changed event is stored | Should | Developer | Not run
AT-095 | M6 | Capture | 8.5 | Quick capture works offline | Airplane mode is on | The user types a thought in Capture and saves it | It appears at the top of the Capture list immediately, showing its date and time | Must | Founder | Not run
AT-096 | M6 | Capture | 8.5 | Newest captures come first | The user captured three thoughts at 9:00 AM, 1:00 PM and 6:00 PM | The user opens Capture | The 6:00 PM entry is at the top and the 9:00 AM entry at the bottom, each showing its date and time | Must | Founder | Not run
AT-097 | M6 | Capture | 8.5 | Edit a capture | A capture reads Call Rahul abut invoice | The user edits it to Call Rahul about invoice | The corrected text is saved and stays after restarting the app | Must | Founder | Not run
AT-098 | M6 | Capture | 8.5 | Delete a capture with Undo | A capture exists | The user deletes it, taps Undo, then deletes it again and lets the Undo window pass | It returns after Undo, and after the second delete it is gone from the list | Must | Founder | Not run
AT-099 | M6 | Capture | 8.5 | Capture from the home-screen widget | The widget is on the home screen | The user taps quick add and types a thought | It is saved to Capture without opening the full app | Must | Founder | Not run
AT-100 | M6 | Capture | 8.5 | Capture from the share sheet | Text is selected in another app, such as Chrome or WhatsApp | The user shares it to Sahai | The text lands in Capture | Must | Founder | Not run
AT-101 | M6 | Capture | 8.5 | Create a stream item from a capture | A capture reads electricity bill due soon | The user taps Create, picks Stream item, Personal › Finance & Bills, group Errands, types Pay electricity bill, saves and picks Remove | The form showed the capture text above it with an empty name field; Pay electricity bill appears in Finance & Bills with group Errands; the capture leaves the list | Must | Founder | Not run
AT-102 | M6 | Capture | 8.5 | Create a project, task or subtask | Three captures exist | The user creates a project from the first, a task in an existing project from the second and a subtask from the third, typing each name and picking Remove | Each appears in the right place with the name the user typed, and all three captures leave the list | Must | Founder | Not run
AT-103 | M6 | Capture | 8.5 | Keep a capture to create more | A capture reads call Rahul, buy milk | The user creates Call Rahul from it and picks Keep, then creates Buy milk from it and picks Remove | The capture stays after the first item and leaves the list after the second; both items exist | Must | Founder | Not run
AT-104 | M6 | Activity log | 9 | Capture events are logged | The user captures a thought and creates two items from it | The developer inspects the log | A captured event is stored, plus one converted event per item, each linking the capture to the new item | Should | Developer | Not run
AT-105 | M7 | Onboarding | 8.1 | Onboarding builds real data | A fresh install | The user completes steps 1 to 3 | They created one or two domains, a project, a task and two subtasks, with no sample data, and the Summary shows only the first subtask | Must | Founder | Not run
AT-106 | M7 | Onboarding | 8.1 | Practice step changes nothing | Onboarding step 4 is finished | The user checks the Summary and the Set-Aside page | The first subtask is TODO and showing; nothing is DONE or set aside | Must | Founder | Not run
AT-107 | M7 | Onboarding | 8.1 | Skip onboarding | Onboarding is on any step | The user taps Skip | The app opens on the Summary and keeps anything already created | Should | Founder | Not run
AT-108 | M7 | Onboarding | 8.1, 8.6 | Replay onboarding | Onboarding was completed earlier | The user picks Replay onboarding in Settings | Onboarding runs again | Should | Founder | Not run
AT-109 | M7 | Settings | 8.6 | Edited presets apply | The user changes Tonight to 9 PM in Settings | The user opens Set aside on a card | Tonight offers 9 PM | Must | Founder | Not run
AT-110 | M7 | Settings | 7, 8.6 | Changing Day starts at | Day starts at is changed to 3:00 AM and it is 3:30 AM | The user picks Tomorrow morning | The wake time is 8 AM the next calendar day | Should | Founder | Not run
AT-111 | M7 | Backup | 3 | Auto Backup restores data | The phone has real data and Google backup is on | A backup runs (or is forced with Android's backup tool), then the app is reinstalled | All data comes back | Must | Developer | Not run
AT-112 | M7 | Backup | 3, 8.6 | Database size warning | The database passes 20 MB | The user opens Settings | A warning shows that backup may stop | Should | Developer | Not run
AT-113 | M7 | Activity log | 9 | Log retention | The log holds events older than 12 months | Compaction runs | Those events become daily summaries and the log stays under 10 MB | Should | Developer | Not run
AT-114 | M7 | Performance | 13 | Fast with 10,000 items | The database holds 10,000 items on a mid-range phone | The user opens the app and completes an item | Cold start to Summary is under 2 seconds and the Summary recomputes in under 50 ms | Must | Developer | Not run
AT-115 | M7 | Offline | 13 | Everything works offline | Airplane mode is on | The user uses every v1 feature | Everything works | Must | Founder | Not run
AT-116 | M7 | Accessibility | 13 | TalkBack support | TalkBack is on | The user completes, sets aside and reorders cards | Every action is announced, and swipe and drag actions have button alternatives | Must | Founder | Not run
AT-117 | M7 | Accessibility | 13 | Large system font | The system font is set to the largest size | The user visits every screen | Nothing is cut off or overlapping | Should | Founder | Not run
AT-118 | M7 | Time | 13 | Set-aside times survive a time-zone change | An item is set aside until 8 AM India time | The phone switches to Dubai time | It wakes at the same moment, shown in local time | Should | Founder | Not run
AT-119 | M7 | Data | 13 | No half-finished changes | The app is mid-way through completing an item | The app is force-closed at that moment | Either the completion and its log event are both saved or neither is | Should | Developer | Not run
AT-120 | M7 | Settings | 8.6 | Send feedback | The user is in Settings | The user taps Send feedback | An email draft opens for the user to write and send | Should | Founder | Not run
AT-121 | M8 | Release | 2, 16 | Testers can install | A build is on a Google Play testing track and a tester is invited | The tester opens the invite link | They can install the app from Google Play | Must | Founder | Not run
AT-122 | M8 | Release | 16 | Privacy policy is linked | The store listing and app are ready | The user checks Play Console and the app's About screen | A privacy policy is linked in both | Must | Founder | Not run
AT-123 | M8 | Release | 16 | Data safety matches the app | The Data safety form is filled in | The user reviews it against the PRD | It states no data is collected or shared | Must | Founder | Not run
AT-124 | M8 | Release | 16 | Icon and name | The release build is installed | The user checks the launcher and the store listing | The final icon and the name Sahai appear | Should | Founder | Not run